## Sheet1
No | Actividad | % | Dias | Inicio | Fin | Responsable | Prerequisitos
23 | Frente Integración
24 | PRE-REQUISITO: Acceso remoto a las maquinas de ESP | 0%
25 | ESP Integration Design Phase | 28% | 14 days | 2017-07-28 08:00 | 2017-08-16 17:00 |  | 4;16;24
26 | Configuration Test for the SMSC Gateway settings for IN and OUT SMS | 40% | 2 days | 2017-07-28 08:00 | 2017-07-31 17:00 | Nicolas Payares
27 | Configuration Test for the SMSC interface of TIAXA, receiving IN messages | 40% | 2 days | 2017-08-01 08:00 | 2017-08-02 17:00 | Nicolas Payares | 26
28 | Specification of Adapter-SMSC-Interface for receiving and sending SMS | 20% | 2 days | 2017-08-03 08:00 | 2017-08-04 17:00 | Nicolas Payares | 27
29 | Specification of Adapter-TIAXA-Interface for sending SMS to shortcut | 20% | 2 days | 2017-08-07 08:00 | 2017-08-08 17:00 | Nicolas Payares | 28
30 | Configuration test for ESP-RTDM integration | 40% | 1 day | 2017-08-09 08:00 | 2017-08-09 17:00 | Nicolas Payares | 29
31 | Configuration test for RTDM- TIAXA integration | 40% | 1 day | 2017-08-10 08:00 | 2017-08-10 17:00 | Nicolas Payares | 30
32 | Specification of ESP-RTDM and RTDM-TIAXA interfaces | 20% | 1 day | 2017-08-11 08:00 | 2017-08-11 17:00 | Nicolas Payares | 31
33 | Entrega doc. Diseño Integracion | 60% | 0 days | 2017-08-11 17:00 | 2017-08-11 17:00 | Nicolas Payares | 32
34 | Aprobación doc Diseño integracion | 0% | 3 days | 2017-08-14 08:00 | 2017-08-16 17:00 | OTECEL | 33
35 | Doc Diseño Integracion Aprobado por OTECEL | 0% | 0 days | 2017-08-16 17:00 | 2017-08-16 17:00 | OTECEL | 34
36 | ESP Integration Construct Phase | 0% | 13 days | 2017-08-14 08:00 | 2017-08-30 17:00 |  | 25FS-3 days
37 | RTDM - TIAXA SMPP Interface | 0% | 3 days | 2017-08-14 08:00 | 2017-08-16 17:00 | Rec. Integracion;Nicolas Payares
38 | RTDM - SMSC SMPP Interface | 0% | 3 days | 2017-08-17 08:00 | 2017-08-21 17:00 | Rec. Integracion;Nicolas Payares | 37
39 | SMSC SMPP - ESP Interface | 0% | 3 days | 2017-08-22 08:00 | 2017-08-24 17:00 | Rec. Integracion;Nicolas Payares | 38
40 | ESP -RTDM | 0% | 1 day | 2017-08-25 08:00 | 2017-08-25 17:00 | Rec. Integracion;Nicolas Payares | 39
41 | Entrega doc. Desarrollo Integracion | 0% | 0 days | 2017-08-25 17:00 | 2017-08-25 17:00 | Rec. Integracion;Nicolas Payares | 40
42 | Aprobación doc Desarrollo integracion | 0% | 3 days | 2017-08-28 08:00 | 2017-08-30 17:00 | OTECEL | 41
43 | Doc Desarrollo Aprobado por OTECEL | 0% | 0 days | 2017-08-30 17:00 | 2017-08-30 17:00 | OTECEL | 42
44 | ESP Integration Test Phase | 0% | 17 days | 2017-08-28 08:00 | 2017-09-19 17:00 |  | 36FS-3 days
45 | END to END tests | 0% | 2 days | 2017-08-28 08:00 | 2017-08-29 17:00 | Rec. Integracion;Nicolas Payares
46 | SMPP Adapter tests | 0% | 2 days | 2017-08-30 08:00 | 2017-08-31 17:00 | Rec. Integracion;Nicolas Payares | 45
47 | TIAXA Adapter Tests | 0% | 2 days | 2017-09-01 08:00 | 2017-09-04 17:00 | Rec. Integracion;Nicolas Payares | 46
48 | Performance and Integration Tests | 0% | 4 days | 2017-09-05 08:00 | 2017-09-08 17:00 | Rec. Integracion;Nicolas Payares | 47
49 | Solution Monitoring and Performance | 0% | 4 days | 2017-09-11 08:00 | 2017-09-14 17:00 | Rec. Integracion;Nicolas Payares | 48
50 | Entrega doc. Pruebas Integracion | 0% | 0 days | 2017-09-14 17:00 | 2017-09-14 17:00 | Rec. Integracion;Nicolas Payares | 49
51 | Aprobación doc Pruebas integracion | 0% | 3 days | 2017-09-15 08:00 | 2017-09-19 17:00 | OTECEL | 50
52 | Doc Pruebas Aprobado por OTECEL | 0% | 0 days | 2017-09-19 17:00 | 2017-09-19 17:00 | OTECEL | 51